## Dashboard
Work Order | Project | Equipment | Description | Equipment Description | Status | (Shut Down Number) | Type | Sched. Start Date | Date Completed | Remarks
5920571 | 2E0397 | 35-HV-0201 | 35RS01-B/A Stroke Test & Replace Valve if Leaking (Duty)- Package | CCT.1 PRIM REACTOR 35-VE-12A FEED ISOLN | Completed | 35VE12-004 | PM | 46237
5920303 | 2E0170 | 35-TIT-0127 | 35RS01-B/A Clean, Inspect & Calibrate (35-TIT-0127)- Package | CCT.1 REACTOR FEED PREHEATER TEMP CNTRL | Completed | 35VE12-004 | BD | 46237
5920302 | 2E0170 | 35-PIT-0125 A | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | DP LEVEL OF 35-VE-11 | In Planning | 35VE12-004 | PM | 46237
5920301 | 2E0170 | 35-PIT-0125 B | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | DP LEVEL OF 35-VE-11 | Scheduled | 35VE12-004 | BD | 46237
5914981 | 2E0397 | 35-HV-0212 | 35RS01-B/A Stroke Test & Replace Valve if Leaking (Duty)- Package | CCT.1 PRIM REACTOR 35-VE-12A FEED ISOLN | In Planning | 35VE12-004 | PM | 46237
5901025 | 2E0397 | 35-FV-0926 | 35RS01-B/A Remove, Inspect & Repair Flow Valve, if Required (35-FV-0926)- Packag | H2S TO SULPHIDE PRIM REAC TKS CCT.1 MASS FLOW CNTRL | Scheduled | 35VE12-004 | BD | 46237
5899053 | 2E0170 | 35-PIT-0207 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 FEED TO PRIM REACTORS PRESS | In Planning | 35VE12-004 | PM | 46237
5899052 | 2E0397 | 35-VE-12A | 35RS01-B/A Remove Blind Primary Reactor (35-VE-12A)- Package | PRIMARY REACTOR | Scheduled | 35VE12-004 | CM | 46237
5895939 | 2E0397 | 35-VE-12B | 35RS01-B/A Install Blind Primary Reactor (35-VE-12B)- Package | PRIMARY REACTOR | In Planning | 35VE12-004 | PM | 46237
5895938 | 2E0397 | 35-HV-0202 | 35RS01-B/A Stroke Test, Remove Valve if Leaking & Install Blind (Standby)- Packa | CCT.1 PRIM REACTOR 35-VE-12B FEED ISOLN | In Progress | 35VE12-004 | CM | 46237
5895902 | 2E0170 | 35-PIT-0125 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTOR FEED PREHEATER PRESSURE | In Planning | 35VE12-004 | PM | 46237
5895901 | 2E0170 | 35-PIT-0338 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 FLASH TANK PRESS | In Progress | 35VE12-004 | PM | 46237
5895900 | 2E0170 | 35-PIT-0303 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTORS 35-VE-14&15 VENT GAS PRESSURE | In Planning | 35VE12-004 | PM | 46237
5895899 | 2E0170 | 35-PIT-0313 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTOR VENT HEADER PRESS CTRL | In Planning | 35VE12-004 | BD | 46237
5895897 | 2E0397 | 3500-01-00-01 | 35RS01-B/A Isolation & Blinding Activities For Reactor Swap- Package | Sulphide Précipitation Circuit no. 1 | In Planning | 35VE12-004 | PM | 46237
5895896 | 2E0397 | 35-HV-0227 | 35RS01-B/A Stroke Test, Remove Valve if Leaking & Install Blind (Standby)- Packa | CCT.1 PRIM REACTOR 35-VE-12B FEED ISOLN | Scheduled | 35VE12-004 | BD | 46237
5895895 | 2E0397 | 35-VE-14 | 35RS01-B/A Change Over Primary Reactor Spool-100D- Package | REACTOR | In Planning | 35VE12-004 | PM | 46237
5889840 | 2E0170 | 35-FE-0924 | 35RS01-B/A Remove & Inspect Flow Element (35-FE-0924)- Package | MAKE-UP H2S TO CCT.1 MASS FLOW | In Progress | 35VE12-004 | BD | 46237
5889839 | 2E0170 | 35-FE-0926 | 35RS01-B/A Remove & Inspect Flow Element (35-FE-0926)- Package | H2S TO SULPHIDE PRIM REAC TKS CCT.1 MASS FLOW CNTRL | In Planning | 35VE12-004 | PM | 46237
5873889 | 2E0170 | 35-VE-12A | 35RS01-B/A inspection for flow switch cooling water (35-FISL-0209) | PRIMARY REACTOR | Scheduled | 35VE12-004 | CM | 46237
SHUTDOWN NUMBER
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
STATUS FILTER
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Sheet2
Work Order | Project | Equipment | Description | Equipment Description | Status | (Shut Down Number) | Type | Sched. Start Date | Date Completed | Remarks
5920571 | 2E0397 | 35-HV-0201 | 35RS01-B/A Stroke Test & Replace Valve if Leaking (Duty)- Package | CCT.1 PRIM REACTOR 35-VE-12A FEED ISOLN | Completed | 35VE12-004 | PM | 46237
5920303 | 2E0170 | 35-TIT-0127 | 35RS01-B/A Clean, Inspect & Calibrate (35-TIT-0127)- Package | CCT.1 REACTOR FEED PREHEATER TEMP CNTRL | Completed | 35VE12-004 | BD | 46237
5920302 | 2E0170 | 35-PIT-0125 A | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | DP LEVEL OF 35-VE-11 | In Planning | 35VE12-004 | PM | 46237
5920301 | 2E0170 | 35-PIT-0125 B | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | DP LEVEL OF 35-VE-11 | Scheduled | 35VE12-004 | BD | 46237
5914981 | 2E0397 | 35-HV-0212 | 35RS01-B/A Stroke Test & Replace Valve if Leaking (Duty)- Package | CCT.1 PRIM REACTOR 35-VE-12A FEED ISOLN | In Planning | 35VE12-004 | PM | 46237
5901025 | 2E0397 | 35-FV-0926 | 35RS01-B/A Remove, Inspect & Repair Flow Valve, if Required (35-FV-0926)- Packag | H2S TO SULPHIDE PRIM REAC TKS CCT.1 MASS FLOW CNTRL | Scheduled | 35VE12-004 | BD | 46237
5899053 | 2E0170 | 35-PIT-0207 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 FEED TO PRIM REACTORS PRESS | In Planning | 35VE12-004 | PM | 46237
5899052 | 2E0397 | 35-VE-12A | 35RS01-B/A Remove Blind Primary Reactor (35-VE-12A)- Package | PRIMARY REACTOR | Scheduled | 35VE12-004 | CM | 46237
5895939 | 2E0397 | 35-VE-12B | 35RS01-B/A Install Blind Primary Reactor (35-VE-12B)- Package | PRIMARY REACTOR | In Planning | 35VE12-004 | PM | 46237
5895938 | 2E0397 | 35-HV-0202 | 35RS01-B/A Stroke Test, Remove Valve if Leaking & Install Blind (Standby)- Packa | CCT.1 PRIM REACTOR 35-VE-12B FEED ISOLN | In Progress | 35VE12-004 | CM | 46237
5895902 | 2E0170 | 35-PIT-0125 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTOR FEED PREHEATER PRESSURE | In Planning | 35VE12-004 | PM | 46237
5895901 | 2E0170 | 35-PIT-0338 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 FLASH TANK PRESS | In Progress | 35VE12-004 | PM | 46237
5895900 | 2E0170 | 35-PIT-0303 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTORS 35-VE-14&15 VENT GAS PRESSURE | In Planning | 35VE12-004 | PM | 46237
5895899 | 2E0170 | 35-PIT-0313 | 35RS01-B/A Remove/Declogging/Calibrate/Re-install- Package | CCT.1 REACTOR VENT HEADER PRESS CTRL | In Planning | 35VE12-004 | BD | 46237
5895897 | 2E0397 | 3500-01-00-01 | 35RS01-B/A Isolation & Blinding Activities For Reactor Swap- Package | Sulphide Précipitation Circuit no. 1 | In Planning | 35VE12-004 | PM | 46237
5895896 | 2E0397 | 35-HV-0227 | 35RS01-B/A Stroke Test, Remove Valve if Leaking & Install Blind (Standby)- Packa | CCT.1 PRIM REACTOR 35-VE-12B FEED ISOLN | Scheduled | 35VE12-004 | BD | 46237
5895895 | 2E0397 | 35-VE-14 | 35RS01-B/A Change Over Primary Reactor Spool-100D- Package | REACTOR | In Planning | 35VE12-004 | PM | 46237
5889840 | 2E0170 | 35-FE-0924 | 35RS01-B/A Remove & Inspect Flow Element (35-FE-0924)- Package | MAKE-UP H2S TO CCT.1 MASS FLOW | In Progress | 35VE12-004 | BD | 46237
5889839 | 2E0170 | 35-FE-0926 | 35RS01-B/A Remove & Inspect Flow Element (35-FE-0926)- Package | H2S TO SULPHIDE PRIM REAC TKS CCT.1 MASS FLOW CNTRL | In Planning | 35VE12-004 | PM | 46237
5873889 | 2E0170 | 35-VE-12A | 35RS01-B/A inspection for flow switch cooling water (35-FISL-0209) | PRIMARY REACTOR | Scheduled | 35VE12-004 | CM | 46237

## Sheet3
Row Labels
35VE12-004
Grand Total
Row Labels | Count of Work Order
Completed | 2
In Planning | 10
In Progress | 3
Scheduled | 5
Grand Total | 20